## Basic Template
[7 empty] | Project: |  | CS 340 Project | [17 empty] | Date: 12/03/2013
Project Objective: To develop a working prototype of a game featuring a flying alien
Objectives |  |  |  |  | Major Tasks |  | Project Completed By: 12/03/13 | [19 empty] | Owner
O |  |  |  | 1 | Brainstorming Ideas |  | O | O | [18 empty] | A | B | B | B
O |  |  |  | 2 | Deciding main concept and story |  |  | O | [18 empty] | A | B | B | B
O |  |  |  | 3 | Detailing the shop and game items |  |  |  | O | [17 empty] | A | B | B | B
O |  |  |  | 4 | 2 page summary |  |  |  | O | O | [16 empty] | B | B | B | B
O |  |  |  | 5 | Understanding version control | [5 empty] | O | [15 empty] | B | B | B | B
| O |  |  | 6 | Phase 1 Creating Github Project and adding collaborators | [5 empty] | O | [15 empty] | A | B | B | B
| O |  |  | 7 | Phase 1 Read and watch tutorials on QT, focusing on Qpaint | [5 empty] | O | O | [14 empty] | B | B | B | B
| O |  |  | 8 | Phase 1 Drawing objects in QT | [6 empty] | O | [14 empty] | A
| O |  |  | 9 | Phase 1 Inheritance and classes | [6 empty] | O | [14 empty] | A
| O |  |  | 10 | Phase 1 Alien and sky created | [6 empty] | O | [15 empty] | A | B
|  | O |  | 11 | Phase 2 Multiple Key Presses Enabled | [6 empty] | O | O | [15 empty] | A
|  | O |  | 12 | Phase 2 Enable the Alien to Move up, left, and right | [7 empty] | O | [15 empty] | A
|  | O |  | 13 | Phase 2 Demo Main Menu developed | [8 empty] | O | O | O | O | O | [9 empty] | A
|  | O |  | 14 | Phase 2 Demo Upgrades Shop developed | [8 empty] | O | O | O | O | O | [8 empty] | A
|  | O |  | 15 | Phase 2 Single Flying Object added (plane) | [9 empty] | O | [13 empty] | A
|  | O |  | 16 | Phase 2 More Flying Objects added (moving in different directions) | [10 empty] | O | [12 empty] | A
|  | O |  | 17 | Phase 2 Collision Detection with Flying Objects added | [11 empty] | O | [11 empty] | A
|  |  | O | 18 | Phase 3 Limited Number of Lives implemented utilizing Collision | [12 empty] | O | [10 empty] | A
|  |  | O | 19 | Phase 3 Sky Background Changed (improved look) | [16 empty] | O
|  |  | O | 20 | Phase 3 Sky Background Tiled Horizontally/Vertically | [16 empty] | O
|  |  | O | 21 | Phase 3 Space simulation created/Spaceship Object implemented | [15 empty] | O | O | [7 empty] | A
|  |  | O | 22 | Phase 3 Background Audio added | [15 empty] | O | O | O | O |  |  |  | A | B
|  |  | O | 23 | Phase 3 Main Menu integrated into the Game | [15 empty] | O | O |  | O |  |  | A
|  |  | O | 24 | Phase 3 Upgrades Shop integrated into the Game | [15 empty] | O | O |  | O
O |  |  |  | 25 | First Presentation | [14 empty] | O | [6 empty] | B | B | B | B
O |  |  |  | 26 | Presentation slides completed | [13 empty] | O |  |  |  |  | O |  |  | A | B | B | B
O |  |  |  | 27 | Final documentation completed (Project website, OPPM sheet) | [13 empty] | O |  | O | O | O | O | [5 empty] | A
O |  |  |  | 28 | Demonstration rehearsal | [18 empty] | O |  |  | B | B | B | B
O |  |  |  | 29 | Final demonstration | [19 empty] | O |  | B | B | B | B
# People working on the project: 4
Design & Document | Agile phase 1 | Agile phase 2 | Agile phase 3 |  |  |  | 09/13 | 09/16 | 09/20 | 09/26 | 09/30 | 10/07 | 10/14 | 10/21 | 10/26 | 10/29 | 11/05 | 11/08 | 11/12 | 11/13 | 11/19 | 11/22 | 11/26 | 12/03 | 12/04 | 12/06 | Chris Tobias | Junce Zhao | Ben Bachtler | Brandon Shaver
[13 empty] | O | expected task activity here |  |  |  |  | A = primary owner
[13 empty] | O | no progress or stuck |  |  |  |  | B = secondary owner
[13 empty] | O | in progress
[13 empty] | O | completed
Version 03/19/2010 of the OPPM sheet
Adapted from OPPM: www.onepageprojectmanager.com
Major Tasks
Summary & Forecast
Objectives
Target Dates
Key