## Basic Template
[7 empty] | Project: |  | CS 340 project | [12 empty] | Date: 11/05/2013
Project Objective: To a prototype demonstration
Objectives |  |  |  |  | Major Tasks |  | Project Completed By: 04/3/2010 | [11 empty] | Owner
O |  |  |  | 1 | Phase 1 Brainstorming Ideas |  | O | [11 empty] | A | B | B | B
O |  |  |  | 2 | Phase 1 Deciding main concept and story |  |  | O | [10 empty] | A | B | B | B
| O |  |  | 3 | Phase 1 Detailing the shop and game items |  |  |  | O | [9 empty] | A | B | B | B
| O |  |  | 4 | Phase 1 Choosing different roles | [13 empty] | A
| O |  |  | 5 | Phase 1 2 page summary |  |  |  |  | O | [8 empty] | A
|  | O |  | 6 | Phase 2 Understanding version control | [5 empty] | O | [7 empty] | A
|  | O |  | 7 | Phase 2 Creating Github Project and adding collaborators | [6 empty] | O | [6 empty] | A
|  | O |  | 8 | Phase 2 Reading and watching tutorials on QT | [6 empty] | O | [6 empty] | A
|  | O |  | 9 | Phase 2 Continuing tutorials, focusing on Qpaint | [6 empty] | O | [7 empty] | A
|  | O |  | 10 | Phase 2 Drawing objects in QT | [6 empty] | O | [8 empty] | A
|  | O |  | 11 | Phase 2 Inheritance and classes | [6 empty] | O | [9 empty] | A
|  | O |  | 12 | Phase 2 Alien and sky created | [7 empty] | O | [6 empty] | A
|  | O |  | 13 | Phase 2 feature 3 unit tested | [7 empty] | O | [7 empty] | A
|  | O |  | 14 | Phase 2 feature 4 unit tested | [7 empty] | O | [8 empty] | A
|  |  | O | 15 | Phase 3 feature set selected | [8 empty] | O |  |  |  |  | A | B | B | B
|  |  | O | 16 | Phase 3 feature 1 developed | [9 empty] | O |  |  |  |  | A
|  |  | O | 17 | Phase 3 feature 2 developed | [9 empty] | O | [5 empty] | A
|  |  | O | 18 | Phase 3 feature 3 developed | [9 empty] | O | [6 empty] | A
|  |  | O | 19 | Phase 3 feature 4 developed | [9 empty] | O |  |  |  |  | A
|  |  | O | 20 | Phase 3 feature 1 unit tested | [10 empty] | O |  |  |  |  | A
|  |  | O | 21 | Phase 3 feature 2 unit tested | [11 empty] | O |  | A | B | B | B
|  |  | O | 22 | Phase 3 feature 3 unit tested | [10 empty] | O |  |  | A
|  |  | O | 23 | Phase 3 feature 4 unit tested | [11 empty] | O |  | A
O |  |  |  | 24 | Presentation slides completed | [10 empty] | O |  |  | A
O |  |  |  | 25 | Final documentation completed | [12 empty] | O | A
O |  |  |  | 26 | Demonstration rehearsal | [11 empty] | O |  | A | B
O |  |  |  | 27 | Final demonstration | [12 empty] | O | A | B
|  |  |  | 28 | [14 empty] | A | B | B | B
|  |  |  | 29 | [14 empty] | A | B | B | B
# People working on the project:
Design & Document | Agile phase 1 | Agile phase 2 | Agile phase 3 |  |  |  | 09/12 | 09/19 | 09/26 | 10/03 | 10/10 | 10/17 | 10/24 | 10/31 | 11/07 | 11/14 | 11/21 | 11/28 | Chris Tobias | Junce Xchao | Ben Bachtler | Brandon Shaver
[7 empty] | 10/24: O; 10/31: expected task activity here | A = primary owner
[7 empty] | 10/24: O; 10/31: no progress or stuck | B = secondary owner
[13 empty] | O | in progress
[13 empty] | O | completed
Version 03/19/2010 of the OPPM sheet
Adapted from OPPM: www.onepageprojectmanager.com
Major Tasks
Summary & Forecast
Objectives
Target Dates
Key